## Slide 1: West-Life Services overview WP4/5
Alexandre Bonvin, Utrecht University
Madrid, May3/4 2018

## Slide 3: West-Life services benefits to end users
Seamless and transparent access to compute e-Infrastructure (grid / cloud / storage), single-sign-on solutions/implementations (WP4)
Access to user-friendly web portals that facilitates the use of complex software and workflows and guide the choices to be made and the interpretation of results (WP5)
Aggregated access at a single location to documentation and tutorials (WP5)
Support center (WP5)
Aggregated access to their data via the virtual folder mechanism (WP5/6)

## Slide 4: West-Life Operation and maintenance of the computing and data infrastructure WP4

## Slide 5: T4.1: Consolidation and operation of the infrastructure
34 grid sites (31 in EU) as taken from VAPOR monitoring tool, but currently only 24 properly accounted by EGI accounting portal

## Slide 6: T4.1: Consolidation and operation of the infrastructure
Resources in EGI HTC platform (aka grid), available to enmr.eu VO
  34 sites, 90,000 CPU cores available in best effort
  SLA extended until 12/2020: 5 sites, 53 Million CPU hours (6000 CPU years), 54 TB storage
  GPU support at CIRMMP and Queen Mary University
EGI Federated Cloud resources
  support by 4 sites: INFN, CESNET/MU, IISAS, STFC
  SLA extended until 12/2020: 2 sites (INFN and CESNET/MU), up to 160 VCPUs, 3 TB storage
  GPU support at IISAS (OpenStack) and CESNET/MU (OpenNebula)
Onedata storage (14 TB) at INFN
Grid/cloud related user support via EGI GGUS (79 tickets solved)

## Slide 7: T4.1: Consolidation and operation of the infrastructure
Infrastructure usage over project duration:
HTC:
52 Million CPU hours
8.5 Million HTC jobs
Cloud
0.55 Million Wall time hours
3262 Virtual Machines

## Slide 8: T4.2: Consolidation of job management mechanisms
West-life Virtual Folder
  Service and portal components to unify access to datasets
  ARIA authentication, W-l SSO in progress
  EUDAT B2DROP integration
  Prototype Onedata integration
    Use metadata service to track directories and files
    Oneclient to mount different Oneprovider sites on local webDAV area
  Direct access to PDB and PDB-REDO
  Used by DISVIS and Scipion Web Tools
T4.3: Programmatic Access to datasets
3 portals make now use of DIRAC4EGI (HADDOCK/CS-Rosetta/AMBER)

## Slide 9: T4.4: Unified security and accounting model
IdP-SP proxy (auth.west-life.eu)
  Connect with identity providers (ARIA, …, Google)
  Provide consolidated identities to services
    Using Perun (CESNET+MU) identity management
  SAML and OpenID Connect protocols
16 registered services
  8 end-user portals, Openstack & Onedata (INFN), and internal/experimental services
Following technology of ELIXIR AAI
Legal and formal steps
  Fixed Acceptable Usage Policy
  User’s consent (GDPR)
Accounting support
  Leverage trust between Proxy and services
  Utilize EGI accounting schemas & tools

## Slide 10: WP4 deliverables
Period I
  D4.1: Consolidated architecture of job submission and interaction with infrastructure
  D4.1 Common security model design
  D.4 Report on experience with consolidated platform and its interaction with infrastructure
  D4.4 Overview of external datasets, strategy of access methods, and implications on the portal architecture.
Period II to date
  D4.5 Report on the progress of the deployment of the consolidated platform and its interactions with infrastructure
Forthcoming
  D4.6 Final report on deployment of consolidated platform and the overall architecture

## Slide 11: WP4 KPIs
https://about.west-life.eu/network/west-life/about/project,
at 16:40 1 May 2018

## Slide 12: AAI infrastructure highlights
WestLife Architecture presented at DI4R in Brussels
New functions introduced
  Support for OpenId Connect protocol
  (in addition to SAML)
Integration in EGI fedcloud
Integration in Onedata

## Slide 13: West-Life Virtual Research Environment WP5

## Slide 14: WP5 – objectives
O5.1: Deployment and operation of the West-Life-VRE portal
O5.2: Establishment and operation of the West-Life-VRE support and expertise center for users and software developers, covering all VRE areas
O5.3: Provision of information and training material covering all VRE areas and offered services.
O5.4: Development and integration of new service portals.
O5.5: Provision of customized end-users VMs and/or containers for various applications.

## Slide 15: T5.1 Deployment and operation of the West-Life-VRE portal
Single entry point for all our services: west-life.eu
Hosted and built on the ARIA CMS from INSTRUCT (ensures sustainability)

## Slide 16: T5.1 Deployment and operation of the West-Life-VRE portal
Entry point for all our services (several inherited from WeNMR)

## Slide 17: T5.1 Deployment and operation of the West-Life-VRE portal
Crystallography services

## Slide 18: T5.1 Deployment and operation of the West-Life-VRE portal
Electron microscopy services

## Slide 19: T5.1 Deployment and operation of the West-Life-VRE portal
NMR services
Most are WeNMR legacy – in active use and maintained/ further developed

## Slide 20: T5.1 Deployment and operation of the West-Life-VRE portal
D5.6 Virtual machines
Already used for several workshops
(INSTRUCT Utrecht Apr. 2016; NeCEN, Leiden, ISCG2017, Taipei)

## Slide 21: T5.1 Deployment and operation of the West-Life-VRE portal
D5.6 Virtual machines
West-Life VM – usage of CernVM technology
  Minimalistic CernVM 4.0 image
  (18 MB)
  Operating system (Scientific Linux 7.x) and all software available via cernvmfs
  /cvmfs/west-life.egi.eu/software
  /cvmfs/wenmr.egi.eu/
  …
  Software is downloaded, cached transparently on request
  CCP4, SCIPION, WENMR
  West-Life Virtual Folder, Repository,…
Already used for several workshops
(INSTRUCT Utrecht Apr. 2016; NeCEN, Leiden, ISCG2017, Taipei)

## Slide 22: T5.1 Deployment and operation of the West-Life-VRE portal
Virtual folder portal (SSO via ARIA) – current support for B2DROP, Dropbox, WebDav services

## Slide 23: T5.2 - Knowledge and support center
The portal integrates both internal forum functionalities (a very recent development – no usage stats) and links to external forums in use

## Slide 24: T5.2 - Knowledge and support center
HADDOCK forum in collaboration with the BioExcel CoE (ask.bioexcel.eu)

## Slide 25: T5.2 - Knowledge and support center
For any e-infra related requests (e.g. grid or cloud-related) we use the GGUS portal
56 tickets handled in the 1st year

## Slide 26: T5.2 - Knowledge and support center
Various online tutorials aggregated in the support center

## Slide 27: T5.3 Development and integration of new service portals
Three new portals added in 2017:
  SpotON: prediction of hot-spot residues in protein complexes
https://milou.science.uu.nl/services/SPOTON

## Slide 28: T5.3 Development and integration of new service portals
Three new portals added in 2017:
  3DBionotes: Web application to automatically annotate biochemical and biomedical information onto structural models

## Slide 29: T5.3 Development and integration of new service portals
Three new portals added in 2017:
  DipCheck: A validation tool for the evaluation of protein backbone geometry
Pereira J, Lamzin VS.
IUCrJ (2017) 4, 657-670

## Slide 30: T5.3 Development and integration of new service portals
Several 3rd party services (external to the project) have been included upon request from their developers
Services have been registered in ELIXIR bio.tools (searchable from the VRE)

## Slide 31: T5.4 - Customized end-users VMs
The virtual folder portal (see T5.1) is an example of customized VM
Other VMs in EGI AppDB: Scipion (see T5.1) and a standalone Virtual folder VM (more in WP6)
https://appdb.egi.eu/

## Slide 32: Consolidation / update of existing portals

## Slide 33: Xplor-NIH put back into production

## Slide 34: AMBER
Implemented features for/with West-Life:
  consolidation of portal machinery
  connection to grid / DIRAC4EGI
  connection to data (e.g. via the VirtualFolder mechanism)

## Slide 35: CCD2
Implemented features for/with West-Life:
Migration to modern development environment
New front end design with extended functionality
ARIA and West-Life login
Ability to save results locally and on shared folder

## Slide 36: PDB-REDO
Implemented features for/with West-Life:
Consolidated web server and databank
mmCIF support on data in and data out
Full databank update (>100k entries; 1Mhr CPU-time)
ARIA and West-Life SSO
User-initiated databank updates (registered users or SSO)
Interfaced with CCP4 online and ARP/wARP (server)
Interfaced with 3D-Bionotes and PDBe (databank)

## Slide 37: Consolidation and operation of the infrastructure - Web Portals (UU)
Migration from several standalone services to a single base server with individual services as optional modules
Portal base
  Provides general layout, styles, and utility scripts and static pages
  Central user management (Flask-Login, SSO)
    Personal User pages (Job monitoring/management, Profile management )
  Administration interface
Services
  Define custom views and forms
  Registered via portal configuration

## Slide 38
Migration from local provisioning to provisioning via docker-compose
Improves portability and development
Separation of the different components
Important configuration stored in docker compose file
Easy to switch between development/production configuration
Easy scaling by deploying to a docker swarm
Consolidation and operation of the infrastructure - Web Portals (UU)
User database
Web portal
Static content
SSL

## Slide 39: User satisfaction
Implementation of a simple user satisfaction survey in a number of portals
Sample code and documentation in GitBook
  https://h2020-westlife-eu.gitbook.io/satisfaction-plugin
Some stats (Since April 8th)
  HADDOCK 4.8 (114 respondents)
  DISVIS 5.0 (2 respondents)
  PowerFit 5.0 (2 respondents)
  SpotON 4.9 (7 respondents)

## Slide 40
Building bridges between services

## Slide 41: Scipion – PowerFit workflow

## Slide 42: FANTEN – HADDOCK workflow

## Slide 43: Connecting portals to data repos
west-life.eu

## Slide 44: Connecting portals to data repos

## Slide 45: Connecting portals to data repos
SSO authentification via INSTRUCT-ERIC

## Slide 46: Connecting portals to data repos
Allows to aggregate storage providers

## Slide 47: Connecting portals to data repos
Allows to browse storage

## Slide 48: Connecting portals to data repos

## Slide 49
Connecting portals to data repos
Upload now also possible

## Slide 50
AMBER
FANTEN
XPLOR-NIH
CS-ROSETTA
GROMACS
DISVIS
HADDOCK
SpotON
SCIPION
POWERFIT
PDB-REDO
CCD
ARP/WARP
AUTORICKSSHAW
CCP4online
VICI
3DBionotes
DipCheck
OneData/
EUDAT/PDB
SSO

## Slide 51: WP5 output and KPIs

## Slide 52: WP5 - Milestones

## Slide 53: Deliverables
Notes: " D5.4 "Report on the activities of the help desk" is also delayed. We are reviewing how best to complement the established user help resources in this field. The delay in the operational launch of the portal delayed the helpdesk planning. Identification and focused work on use cases also create the need for a targeted helpdesk approach. New staff recruitment and advancement of the portal implementation now allows us to engage with this as a priority, and we will deliver D5.4 in September."

## Slide 54: KPIs for WP5
#services integrated in the VRE portal (% increase with respect to previous report)
  Previous (D5.2): 22 portals Current (D5.7): 23 +4%
#tutorials and use cases (% increase with respect to the previous report)
  Previous: 11 tutorials Current 15 +36%
  https://about.west-life.eu/network/west-life/support/tutorials

## Slide 55: KPIs for WP5 – usage stats
* not in production in 2017

## Slide 56: Impact: HADDOCK
Total Users: 10312 EU Users: 2201 (21.3%) # of countries: 87

## Slide 57: Impact: DISVIS
Total Users: 220 EU Users: 105 (47.7%) # of countries: 36

## Slide 58: Impact: PowerFit
Total Users: 113 EU Users: 36 (31.9%) # of countries: 30

## Slide 59: Impact: SpotON
Total Users: 153 EU Users: 60 (39.2%) # of countries: 30

## Slide 60: Impact: PDB-REDO.EU
>1800 registered users (map) and 17k unique visitors/month

## Slide 61: Impact: ARP-Warp

## Slide 62: WP5 - Conclusions
Very much improved branding of our entry portal
Gaining visibility: We are getting requests to integrate 3rd party services
World wide impact
New portals have been developed
Most portals are well used

## Slide 63: Questions/discussion

## Slide 65: AAI infrastructure summary
Standard service components
  Identity management based on Perun
    Operated by CESNET/Masaryk University
  IdP-SP-Proxy (auth.west-life.eu) providing interface to services
    Technology aligned with ELIXIR
  Follows technologies of ELIXIR AAI
Architecture presented at DI4R in Brussels

## Slide 66: AAI recent development
New functions introduced
  Support for OpenId Connect protocol (in addition to SAML)
  Easier for end-services
16 portals registered with the Proxy
“Acceptable Usage Policy” fixed
The West-Life application form extended
  User’s consent (GDPR), AUP

## Slide 67: AAI future work
Improved coverage of AAI
  Integration of additional end services
Support for accounting
  Leverage trust relationship between Proxy and services
  Introduce framework to collect usage records
  Utilize EGI accounting schemas/tools where possible

## Slide 68: West-Life SSO in EGI Federated Cloud
The EGI Fed-Cloud site in Padova supports many authentication systems: Openstack native, Indigo IAM, West-Life SSO
The West-Life SSO pilot service is based on Secure Assertion Markup Language v.2 (SAML)
The Openstack Federated Identity API (OS-Federation) is used for both Indigo IAM and West-Life SSO
The configuration of the Openstack Identity Service (Keystone) has been changed in order to be compliant with the requirements from West-Life:
http://internal-wiki.west-life.eu/index.php/Enabling_SAML2_for_end_services
The framework Shibboleth is used for dealing with SAML handshake

## Slide 69: West-Life SSO in Onedata
Federated login in Onezone is based on OpenId Connect (OIDC)
The West-Life SSO team makes available a pilot OIDC endpoint:
https://auth.west-life.eu/oidc
A pre-production installation of Onezone with the support to West-Life SSO is available at CNAF-INFN (Bologna)
Steps required for the integration:
Developed a West-Life SSO plugin for the business logic of Onezone (Erlang)
Updated the front-end (Ember.js) of Onezone with West-Life specific definitions (style-sheet, logo)

## Slide 70
The integration consists of:
  A plugin for the metadata service, tracking directories and files
  An extension of the front-end, based on Aurelia framework, handling user credentials
  The oneclient, it mounts spaces from different Oneprovider sites on the local webDAV area
The credential required is the access token created by the Onezone service
Integration “Virtual Folder” – Onedata /1

## Slide 71
Status
The plugin for the metadata service is quite ready
Some troubles mounting the spaces and the renewal of the access token
Front-end not yet implemented
For further details:
https://issues.infn.it/jira/browse/EOSCHUBPD-1
Integration “Virtual Folder” – Onedata /2

## Slide 72: Scipion in the cloud
(Almost) contradicting requirements
  Complex software framework, many dependencies
  Resource requirements beyond usual user desktop
  Interactivity, including 3D rendering
Deployment via Cloudify
  Access the cloud resources
  Install the right software, resolve dependencies
GPU support
  Available at some EGI cloud sites, supported by OCCI
  Remote access with VirtualGL + TurboVNC
Still not so user friendly

## Slide 73: Scipion in the cloud
Manage the deployment with web portal
  RESTful API keeping track of Cloudify deployments
  JS client, including noVNC remote desktop display
Scipion projects on OneData
Try at https://api-dev.scipion.ics.muni.cz/
Submitted paper to ScienceCloud2018